## Slide 1: Basic Improvement Methodology
Review of QI 102: How to Improve with the Model for Improvement

## Slide 2: Lecture Objectives
List the three questions in the Model for Improvement
Identify the key elements of an effective aim statement
Identify three kinds of measures: process, outcome, and balancing measures
Use change concepts and critical thinking tools to come up with good ideas for changes to test
Test changes on a small scale using the Plan-Do-Study-Act (PDSA) cycle

## Slide 3: Lecture Outline
An Overview of the Model for Improvement
Setting an Aim
Choosing Measures
Developing Changes
Testing Changes

## Slide 4: How Can We Improve?
1. Will. You must have the will to improve
2. Ideas. You must have ideas about alternatives to the status quo.
3. Execution. You must make it real.

## Slide 5: How Can We Improve?
1. Will. You must have the will to improve
2. Ideas. You must have ideas about alternatives to the status quo.
3. Execution. You must make it real.

## Slide 6: Improvement Methods
Model for Improvement
Lean
Six Sigma
Having a standard road map for improvement — rather than the specific framework you decide to use — is what’s most important

## Slide 7: Three Questions and a Cycle

## Slide 8: Step 1: Set an Aim
How good?
For whom?
By when?

## Slide 9: Step 1: Set an Aim
How good?
For whom?
By when?
Bold
Realistic
Clear
Concise
Measureable
Meaningful

## Slide 10: Which is the better aim statement?
Reduce all types of hospital-acquired infections by as much as possible, as quickly as possible.
Decrease the rate of hospital-acquired pneumonia for patients in the ICU from 23 infections per 1,000 catheter days to less than 5 infections per 1,000 catheter days by May 1.

## Slide 11: Which is the better aim statement?
Reduce all types of hospital-acquired infections by as much as possible, as quickly as possible.
Decrease the rate of hospital-acquired pneumonia for patients in the ICU from 23 infections per 1,000 catheter days to less than 5 infections per 1,000 catheter days by May 1.

## Slide 12: Step 2: Establish Measures
Outcome measures
Process measures
Balancing measures

## Slide 13: Step 2: Establish Measures
Outcome measures
Process measures
Balancing measures
Where are we going?
What are we doing?
What else is happening?

## Slide 14: Which measure is which?
Average number of times patients receive recommended oral care in 24 hours
Patient and staff satisfaction scores
Rate of hospital-acquired pneumonia per 1,000 catheter days in the ICU

## Slide 15: Which measure is which?
Average number of times patients receive recommended oral care in 24 hours process
Patient and staff satisfaction scores balancing
Rate of hospital-acquired pneumonia per 1,000 catheter days in the ICU outcome

## Slide 16: Step 3: Developing Changes
Process analysis tools
Benchmarking
Technological solutions
Creative thinking
Change concepts

## Slide 17: Change Concepts
Eliminate waste
Improve workflow
Optimize inventory
Enhance the producer-customer relationship
Change the work environment
Manage time
Manage variation
Design systems to prevent errors
Focus on the design of products and services

## Slide 18: What changes could improve oral care in the ICU?
Improve workflow
Optimize inventory
Change the work environment
Manage variation
Design systems to prevent errors
Other ideas?

## Slide 19: What changes could improve oral care in the ICU?
Improve workflow Ensure mouth-cleaning supplies are kept in ready-to-go state
Optimize inventory Ensure toothbrushes, mouthwash, etc. are consistently available
Change the work environment Train hospital staff on proper mouth-cleaning technique and importance
Manage variation Update oral care policy to be consistent with CDC guidelines for all patients
Design systems to prevent errors Post the oral-care protocol in visible places

## Slide 20: Step 4: Testing Changes

## Slide 21: Step 4: Testing Changes
Plan
  Questions & predictions
  Who/what/where/when?
Do
  Observe the test
  Document results
Study
  Draw run charts
  Analyze the data
Act
  Refine the change and plan for the next cycle

## Slide 22: Linking PDSA Test Cycles
Start small
Think ahead
Don’t wait to begin!

## Slide 23: Review: Using the MFI to Improve Care

## Slide 24: Video
http://www.ihi.org/education/IHIOpenSchool/resources/Pages/Activities/PDSACyclesFromCLABSIsToCucumbers.aspx
https://youtu.be/8Q7qnNpTWxM

## Slide 25: Discussion
In the example about CLABSIs, what would be a reasonable next PDSA cycle?
What PDSA cycles do you use in your daily work, even if that’s not the name you use for them?
What’s the value of a failed PDSA cycle?
Think about the last PDSA cycle you ran in your personal life — even if you didn't know it was a PDSA cycle at the time. Was it successful? Why or why not?
http://www.ihi.org/education/IHIOpenSchool/resources/Documents/Facilitator_PDSACyclesFromCLABSIsToCucumbers.pdf

## Slide 26: Exercise
Go to http://www.ihi.org/education/IHIOpenSchool/Courses/Documents/QI102_exercise.pdf and practice planning an improvement project.
Ask a partner to review your work, using the reviewer questions as a helpful guide. Refine your worksheet based on peer feedback.

## Slide 27: Discussion
How did you select your aim, measures, and changes?
What is your level of confidence you will be able to make this change?
How do you think having this written plan will help you?
What did you learn during this activity?
http://www.ihi.org/education/IHIOpenSchool/Courses/Documents/QI102_exercise.pdf